Standard Quarterly Progress Report

For Humanitarian and Standard Programme Documents, submitted with FACE form on quarterly basis

UNICEF Narrative Progress Report (to be completed on paper if CSO partner does not have internet and is unable to access the Partner Reporting Portal, www.partnerreportingportal.org)

| Programme Docu Title |  |  |  |
| --- | --- | --- | --- |
| Programme Docu Ref. No. |  |  |  |
| Organization Name | National Association of Workers in Centers for Special Educational Support |  |  |
| Name of CSO Authorized Official | Milen Nakov |  |  |
| Title of Authorized Official | Chair person |  |  |
| Programme Docu Duration | Start Date: 13 Jan 2025 |  | End Date: 30 June 2026 |
| Reporting Period | From 02/2025 |  | to 04/2025 |
| Programme Budget | PD Currency BGN |  | Value 76,250 BGN |
| UNICEF Cash Contribution | Cash Transfer Currency BGN |  | Value 76,250 BGN |
| Funds Received to Date | Currency, value 18,960 BGN |  | % of total |
| Signature of Authorized Official: |  | Date: |  |

2. Reporting on results achieved

The table provides an overview of results achieved during the reporting period and cumulatively since the onset of the programme.

| Programme Outputs | Performance indicator | Targets | Achievement in reporting period | Cumulative progress to date | Progress status* |  | Narrative assessment/ summary of progress** |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Progr. Output 1 Strengthening the capacity of CSES to support families of children with disabilities and provide direct support through the program "Workshops for parents - Let's grow together PLUS" - Two in-person trainings for facilitators of workshops for parents - Direct support for families of children with disabilities by conducting the "Workshops for parents - Let's grow up together PLUS" program - Provision of supervision for the facilitators | Number of facilitators capacitated to conduct Workshops for parents | Trainings: 2 Trainees: 30+30 | Trainings: 1 Trainees: 29 | 1 Trainees: 29 |  |  | Между 4-ти и 6-ти март 2025, в град Пловдив се проведе обучение за водещи на Работилници за родители „Да пораснем заедно +“. В обучение се включиха 29 педагогически специалисти (27 жени и 2 мъже) от 14 ЦСОП в сраната (Берковица, Благоевград, Варна, Велинград, Габрово, Гоце Делчев, Добрич, Кубрат, Кърджали, Пазарджик, Пловдив, София „Едуард Сеген, Стара Загора, Харманли). Обучаемите бяха настанени в Гранд хотел Пловдив. Обучението се проведе в наета зала в кв. Капана. На участниците бяха осигурени кафе-паузи, кетъринг за обяд и 1 официална вечеря в зала на хотела. Както на обучителите, така и на обучаемите бяха осигурени необходимите материали за провеждане на обучителните сесии. 14 ЦСОП в сраната (Берковица, Благоевград, Варна, Велинград, Габрово, Гоце Делчев, Добрич, Кубрат, Кърджали, Пазарджик, Пловдив, София „Едуард Сеген, Стара Загора, Харманли). стартираха успешно провеждането на „Работилници за родители +“. В Работилниците по проекта се включват общо 136 (от които 123 жени и 13 мъже) на 137 деца (от които 31 момичета и 106 момчета) със СОП, които се обучават в ЦСОП. Подробната информация за участниците с присъствените списъци е изпратена на УНИЦЕФ в приложение към настоящия отчет. |
|  | Number of beneficiaries | Parents: 270 Children: 270 |  |  |  |  |  |
|  | Percentage of parents/caregivers who self-report increased parental capacities by participating in the new parenting support programme | Min 70% |  |  |  |  |  |
|  | Supervision sessions | 4 | 2 | 2 |  |  | На 11.04.2025 г. и 25.04.2025 се проведе супервизия от Керанка Станева за 14 специалисти от ЦСОП (Велинград, Габрово, Гоце Делчев, Добрич, Кубрат, Кърджали и Харманли). На 09.04.2025 г. и 23.04.2025 се проведе супервизия от Емилия Чапкънова за 15 специалисти от ЦСОП (Берковица, Благоевград, Варна, Пазарджик, Пловдив, София и Стара Загора). |
| Progr. Output 2 Situational analysis 2.1. Preparation of situation analysis from external consultant 2.2. Conference event | Situational analysis report is available, and recommendations to inform Inclusive education standard are discussed with the MoES and other stakeholders | YES |  |  |  |  | Тази дейност ще стартира през второто тримесечие на проекта |
|  | Conference validation event is conducted |  |  |  |  |  |  |
| Progr. Output 3 3.1. Identify a minimum of 6 cases to promote practices and share experiences | HIS delivered to UNICEF | 6 |  |  |  |  | Идентифицирането на случаи за популязиране на опита ще се проведе след края на първия цикъл работилници. |
| Effective and efficient programme management | Quarterly narrative and financial reports | 12 | 2 | 2 |  |  | Изпратени 1 технически и 1 финансов отчет |
| Challenges / bottlenecks faced in the reporting period | В процес на изпълнение на дейността 1.1 един от предварително планираните ЦСОП в гр. Ловеч не се включи в обучението поради непредвидени ситуации в екипа на центъра. |  |  |  |  |  |  |
| Proposed way forward in the reporting period | Във втория етап на проекта, могат да се включат допълнително центрове като общия брой не надвишава 20 центъра във второто обучение. |  |  |  |  |  |  |
| Partner Non-financial contribution during reporting period |  |  |  |  |  |  |  |
| Partner Financial contribution during reporting period | Транспортните разходи на обучителите са поети от бюджета на НАРЦСОП; Транспортните разходи на всеки един от участниците в обучението са за сметка на образователната институция - център Currency: BGN |  |  |  |  | Value: 97,05 лв. |  |

3. Overall partnership experience (only for final progress report)

This section to be filled by partner to share overall experience during the implementation as part of final (last) progress report at the end of Programme Document.

| During the course of programme implementation, did UNICEF release cash in a timely manner? | YES NO | Comments: |
| --- | --- | --- |
| During the course of programme implementation, did UNICEF release programme supplies in a timely manner? | YES NO | Comments: |
| During the course of programme implementation, did UNICEF provide timely feedback on FACE forms and narrative progress reports? | YES NO | Comments: |
| During the course of programme implementation, did UNICEF staff respond to queries and requests for technical assistance in a timely manner? | YES NO | Comments: |
| Were joint monitoring and assurance activities implemented as planned in the Programme Document? | YES NO | Comments: |
| Dd your organization and UNICEF take action to address findings identified in monitoring and assurance activities? | YES NO | Comments: |
| Overall, how satisfied was your organization with its partnership with UNICEF on this Programme Document? | Very unsatisfied Unsatisfied Neutral Satisfied Very Satisfied | Comments: |

| FOR UNICEF OFFICE USE ONLY | Rating* | Comment if applicable |
| --- | --- | --- |
| Overall progress of the programme document |  |  |
| Name and signature of UNICEF PD focal point: Title: Date: |  |  |

*For the progress report, status/rating as follows: 	For the final report, status/rating as follows

| On track |  | Achieved as planned |
| --- | --- | --- |
| Constrained |  | Not achieved as planned |
| No progress |  |  |
| Met |  |  |